## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | tarun | 2025-10-10 | Low accuracy in helmet detection | 2 | tarun | High | Retrained YOLO model | 2025-10-09 | closed | no remark
2 | tarun | 2025-10-19 | SQLite not saving violations | 4 | tarun | High | Fixed Pandas | 2025-10-17 | closed | no remark

## Sheet2
Logical
User Interface
Maintainability
Standards
Others